## Summary
WBS Estimate for |  | Product and Channel Review
Version |  | 1.0 | Date | 2012-04-09
Estimated by |  |  | Approved by
Red Hat Approval date
Note: Fill up the cells with white colour only
I. Estimates
1. Total Project Effort (person days) |  | 316
2. Project Duration (months) |  | Max duration |  | max duration that will not impact the quality and the estimate
|  | Min duration |  | min duration that will not impact the quality and the estimate
|  | Suggested duration | 8 | This is the suggested duration for optimal project quality
II. Scope & Assumptions
1. In scope
The scope for estimate does include the following items:
Item |  |  |  | Note
Refer to the session "In Scope" of the BCR 1779 19-03-2012v0.3.pdf document
1
2
3
4
Please refer to "WBS Estimation" for the detailed list of scope items
2. Out of scope
The estimate does not include the following items:
Item |  | Reason |  | Note
1 | Refer to the session "Out of Scope" of the BCR 1779 19-03-2012v0.3.pdf document
2
3
3. Input from Client
The following input are expected to be provided by the customer
Item |  |  | Expected date
1
2
4. Risks
For all the identified risks please refer to risk assessment sheet
For the breakdown of efforts for risk mitigation, please see in "WBS Estimation" sheet
5. Onsite visits and other expenses
The following onsite visits and expenses are expected
Item |  |  | Expected cost
1
2
3
6. Others assumptions
1 | This estimate is based on our standard non-functional requirements (enclosed)
2 | Interface of existing system (which this system will integrated in) is available before project starts
3
III. Milestone Plan
ID | Title/Description | Date | Deliverables | Dependencies
M0 | Kick-Off | D | Meeting minutes | Contract signed
M1 | Project Initiation Finished | D+5.0 weeks | Agreed PID, Full requirements & prototype | M0, all parties approve PID, Full requirements & prototype
M2 | Coding Finished | D+17.0 weeks | Software package | M1
M3 | Testing Finished | D+20.0 weeks | Software package, Test report | M2
M4 | UAT Finish | D+26.0 weeks | Software package | M3
Note on C22: t: We do not expect to input the full scope specification here, instead we refer to some document or email and also the detailed WBS Estimation sheet.
Note on C33: t: This is the list of key out of scope items for those we have a feeling that client may assume that they are in scope. Sample list of out of scope items: - Data migration - Data error correction - User's help - End users training - Testing the web based system in more than <specific number> of standard browsers.
Note on D70: t: mandatory
Note on D71: t: mandatory

## WBS Estimation
WBS Approach for Estimation for Product and Channel Review
Note: Fill up the cells with white colour only
Step 1: Estimate Coding & Unit Test Effort
| Total Coding & Unit Test Effort | 109.25 |  | person days
# | Task Name | Coding Effort | Total Effort | PM | BA | TL & SA | QA | Dev | Tester | Others | Remarks
1 | Create application framework |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | Create common persistence layer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 | Configure using Maven2, Log4j |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | Configure to implement Junit |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 | Configure to write a webservice |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Rates Request |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Create XML file | 0.25 | 0.72311 | 0.072311 | 0.072311 | 0.079542 | 0 | 0.27478 | 0.16632 | 0.057849
2.2 | Create XSD file | 0.5 | 1.4462 | 0.14462 | 0.14462 | 0.15908 | 0 | 0.54957 | 0.33263 | 0.1157
2.3 | Model, Model XML | 0.5 | 1.4462 | 0.14462 | 0.14462 | 0.15908 | 0 | 0.54957 | 0.33263 | 0.1157
2.4 | Create Persistence: DAO, DAO implement | 2 | 5.7849 | 0.57849 | 0.57849 | 0.63634 | 0 | 2.1983 | 1.3305 | 0.46279
2.5 | Apply Junit on Persistence | 2 | 5.7849 | 0.57849 | 0.57849 | 0.63634 | 0 | 2.1983 | 1.3305 | 0.46279
2.6 | Web service |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| SUCCESS response | 2 | 5.7849 | 0.57849 | 0.57849 | 0.63634 | 0 | 2.1983 | 1.3305 | 0.46279
| FAILURE RESPONSE MESSAGES FOR DATA SENT BY THE BROKER | 1 | 2.8924 | 0.28924 | 0.28924 | 0.31817 | 0 | 1.0991 | 0.66526 | 0.2314
| FAILURE RESPONSE MESSAGES FROM SYSTEM VALIDATIONS | 1 | 2.8924 | 0.28924 | 0.28924 | 0.31817 | 0 | 1.0991 | 0.66526 | 0.2314
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Loan Quote Request |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 |  | 5 | 14.4622 | 1.4462 | 1.4462 | 1.5908 | 0 | 5.4957 | 3.3263 | 1.157
3.2 |  | 10 | 28.9245 | 2.8924 | 2.8924 | 3.1817 | 0 | 10.9913 | 6.6526 | 2.314
3.3 |  | 5 | 14.4622 | 1.4462 | 1.4462 | 1.5908 | 0 | 5.4957 | 3.3263 | 1.157
3.4 |  | 5 | 14.4622 | 1.4462 | 1.4462 | 1.5908 | 0 | 5.4957 | 3.3263 | 1.157
3.5 |  | 5 | 14.4622 | 1.4462 | 1.4462 | 1.5908 | 0 | 5.4957 | 3.3263 | 1.157
3.6 |  | 5 | 14.4622 | 1.4462 | 1.4462 | 1.5908 | 0 | 5.4957 | 3.3263 | 1.157
3.7 |  | 3 | 8.6773 | 0.86773 | 0.86773 | 0.95451 | 0 | 3.2974 | 1.9958 | 0.69419
3.8 |  | 3 | 8.6773 | 0.86773 | 0.86773 | 0.95451 | 0 | 3.2974 | 1.9958 | 0.69419
3.9 |  | 3 | 8.6773 | 0.86773 | 0.86773 | 0.95451 | 0 | 3.2974 | 1.9958 | 0.69419
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Loan Creation Request (includes Facility Fee service) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 |  | 10 | 28.9245 | 2.8924 | 2.8924 | 3.1817 | 0 | 10.9913 | 6.6526 | 2.314
4.2 |  | 5 | 14.4622 | 1.4462 | 1.4462 | 1.5908 | 0 | 5.4957 | 3.3263 | 1.157
4.3 |  | 3 | 8.6773 | 0.86773 | 0.86773 | 0.95451 | 0 | 3.2974 | 1.9958 | 0.69419
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Redemption Quote Request |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.1 |  | 5 | 14.4622 | 1.4462 | 1.4462 | 1.5908 | 0 | 5.4957 | 3.3263 | 1.157
5.2 |  | 3 | 8.6773 | 0.86773 | 0.86773 | 0.95451 | 0 | 3.2974 | 1.9958 | 0.69419
5.3 |  | 3 | 8.6773 | 0.86773 | 0.86773 | 0.95451 | 0 | 3.2974 | 1.9958 | 0.69419
5.4 |  | 10 | 28.9245 | 2.8924 | 2.8924 | 3.1817 | 0 | 10.9913 | 6.6526 | 2.314
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Amend Payment Schedule Request |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6.1 |  | 5 | 14.4622 | 1.4462 | 1.4462 | 1.5908 | 0 | 5.4957 | 3.3263 | 1.157
6.2 |  | 3 | 8.6773 | 0.86773 | 0.86773 | 0.95451 | 0 | 3.2974 | 1.9958 | 0.69419
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Cancellation Request |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.1 |  | 3 | 8.6773 | 0.86773 | 0.86773 | 0.95451 | 0 | 3.2974 | 1.9958 | 0.69419
7.2 |  | 3 | 8.6773 | 0.86773 | 0.86773 | 0.95451 | 0 | 3.2974 | 1.9958 | 0.69419
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Change of Bank Details Request |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.1 |  | 3 | 8.6773 | 0.86773 | 0.86773 | 0.95451 | 0 | 3.2974 | 1.9958 | 0.69419
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Mid Term Adjustment Request |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.1 | Persistence |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Just display the form
| a. Define entity class | 4h | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Columns added / removed
| b. Define DAO interface | 0.5h | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| c. Implement DAO |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| i. Create | 0.5h | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
| ii. Read | 1h
| iii. Update | 0.5h
| iv. Delete | 2h
| d. Unit testing | 1d
9.2 | Web service
| a. Define Input XML | 4h
| b. Parse Input XML | 1d
i. Create XML object by JAXB
c. Generate Output XML
| i. Create XML object by JAXB | 4h
ii. Get data from DB with constraints
| d. Generate Failure Response by Broker XML | 4h
i. Create XML object by JAXB
ii. Get data from DB with constraints
| e. Generate Failure Response by Validation XML | 4h
i. Create XML object by JAXB
ii. Check validation
| f. Unit testing | 2d
10 | Report Request
10.1 | Persistence
| a. Define entity class | 4h
| b. Define DAO interface | 0.5h
c. Implement DAO
| i. Create | 0.5h
| ii. Read | 1h
| iii. Update | 0.5h
| iv. Delete | 2h
| d. Unit testing | 1d
10.2 | Web service
| a. Define Input XML | 4h
| b. Parse Input XML | 1d
i. Create XML object by JAXB
ii. Get data from DB with constraints
| c. Generate Output XML | 4h
i. Create XML object by JAXB
| d. Generate Failure Response by Broker XML | 4h
i. Create XML object by JAXB
ii. Get data from DB with constraints
| e. Generate Failure Response by Validation XML | 4h
i. Create XML object by JAXB
ii. Check validation
| f. Unit testing | 2d
| <insert additional lines BEFORE this mark> |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total (man days) | 109.25 | #VALUE! | 31.6 | 31.6 | 34.76 | 0 | 120.08 | 72.68 | 25.28
| Total (man hours) |  | #VALUE! | 252.8 | 252.8 | 278.08 | 0 | 960.64 | 581.44 | 202.24
Step 2: Estimate Total Project Effort before Risk Mitigation
| Total Project Effort before risk mitigation | 287.5 |  | person days
Effort Distribution by Process for this project
| Software Process Name | Effort | Distr. | In Scope | Remarks
1 | Requirement | 28.75 | 10% | Y | < All efforts by process' items during all phases of the development , including UAT & warranty>
2 | Design | 31.625 | 11% | Y
3 | Coding & Unit test | 109.25 | 38% | Y | < Including Unit testing done by developers >
4 | Test | 66.125 | 23% | Y
5 | Deployment | 5.75 | 2% | Y
6 | Customer Support | 5.75 | 2% | Y
7 | Project Management | 28.75 | 10% | Y
8 | Configuration Management | 5.75 | 2% | Y
9 | QA | 5.75 | 2% | Y
100%
Step 3: Mitigation for Named Risks
| Total Mitigation Efforts | 14.375 | 5%
Detailed Risk Mitigation Efforts
| Risk | Man.day | % | Remarks
1 | Requirement is not yet clear | 14.375 | 5% | < please be detailed and specific >
2 |  | 0 | 0% | <don't add risk buffer for unforseen risk, unless agreed with client >
3 |  | 0 | 0% | < best practice is to budget efforts for risk prevention and mitigation + make clear with client on the plan for correction when the risk becomes an issue>
4 |  | 0 | 0% | <Suggested total risk mitigation efforts 5%-20% for WBS estimates>
5 |  | 0 | 0%
6 |  | 0 | 0%
Step 4: SDC Programme Management |  | Man.day | %
| Total SDC efforts | 14.375 | 5% | Remarks
1 | Offshore SDC PM | 14.375 | 5% | For projects with third party supplier, Harvey Nash offshore efforts will be estimated separately here 5% of total efforts or 1.5 days per week should be a norm for a typical development project with 1 Offshore PM
2 |  | 0 | 0%
Step 5: Additional and Specific Effort
| Additional effort | Man.day | % | Remarks
|  | 0 | 0%
1
2
3 |  | 0
4 |  | 0
Step 6: Calculate Total Project Effort
| Total Project Effort | 316 |  | person days | [6 empty] | 38%
Note on E125: Dzung Pham: Project effort distribution
Note on E126: Dzung Pham: Norm = 10%
Note on E127: Dzung Pham: Norm = 11%
Note on E128: Dzung Pham: Norm = 38%
Note on E129: Dzung Pham: Norm = 22% plus 1% others
Note on E130: Dzung Pham: Norm = 2%
Note on E131: Dzung Pham: Norm = 2%
Note on E132: Dzung Pham: Norm = 10%
Note on E133: Dzung Pham: Norm = 2%
Note on E134: Dzung Pham: Norm = 2%
Note on E142: Truong: Percentage of effort buffered for risk mitigation. Buffer for correction when the risk became an issue should be discussed in assumptions (summary sheet)

## Effort Breakdown
A | WBS Effort Distribution
Effort distribution by processes (norm)
ID | Software Process Name | Distr. | In scope
1 | Requirement | 0.1 | Y
2 | Design | 0.11 | Y
3 | Coding & Unit test | 0.38 | Y
4 | Test | 0.23 | Y
5 | Deployment | 0.02 | Y
6 | Customer Support | 0.02 | Y
7 | Project Management | 0.1 | Y
8 | Configuration Management | 0.02 | Y
9 | QA | 0.02 | Y
100%
Effort distribution by processes and stages (norm)
For New development projects
|  |  | Initiation | Definition | Solution | Construction | Transition | Termination | Check
| Process | [6 empty] | (Warranty)
1 | Requirement |  | 25% | 40% | 20% | 10% | 5% | 0% | 100%
2 | Design |  | 10% | 20% | 45% | 20% | 5% | 0% | 100%
3 | Coding & Unit test |  | 4% | 10% | 25% | 42.5% | 12% | 6.5% | 100%
4 | Test |  | 3% | 8% | 25% | 42% | 15% | 7% | 100%
5 | Deployment |  | 5% | 5% | 15% | 30% | 40% | 5% | 100%
6 | Customer Support |  | 5% | 5% | 25% | 30% | 28% | 7% | 100%
7 | Project Management |  | 15% | 20% | 20% | 20% | 20% | 5% | 100%
8 | Configuration Management |  | 10% | 15% | 25% | 31% | 15% | 4% | 100%
9 | QA |  | 10% | 10% | 30% | 30% | 15% | 5% | 100%
| Total |  | 7.91% | 14.54% | 26.1% | 33.43% | 13.02% | 5% | 100%
B | WBS Effort Breakdown
| Total project efforts | 316
| Role | Person days | Person hours | Remarks
| SDC PM | 5 | 40 | aproximation only
| PM | 31 | 248 | aproximation only
| BA | 37 | 296 | aproximation only
| TL & SA | 40 | 320 | aproximation only
| QA | 12 | 96 | aproximation only
| Senior Dev | 24 | 192 | aproximation only
| Dev | 94 | 752 | aproximation only
| Senior Tester | 14 | 112 | aproximation only
| Tester | 58 | 464 | aproximation only
| Total Effort | 315 | 2520 | aproximation only
Efforts by phases
| Phase | Total | Initiation | Definition | Solution | Construction | Transition | Termination (warranty) |  | Remarks
| Person days | 316 | 24.9956 | 45.9464 | 82.476 | 105.6388 | 41.1432 | 15.8 |  | aproximation only
| Person hours | 2528 | 199.9648 | 367.5712 | 659.808 | 845.1104 | 329.1456 | 126.4 |  | aproximation only
Detailed Efforts Breakdown by Process Item over Stages (person days)
|  |  | Initiation | Definition | Solution | Construction | Transition | Termination | Checksum
| Process | [6 empty] | (Warranty)
1 | Requirement |  | 7.9 | 12.64 | 6.32 | 3.16 | 1.58 | 0 | 31.6
2 | Design |  | 3.476 | 6.952 | 15.642 | 6.952 | 1.738 | 0 | 34.76
3 | Coding & Unit test |  | 4.8032 | 12.008 | 30.02 | 51.034 | 14.4096 | 7.8052 | 120.08
4 | Test |  | 2.1804 | 5.8144 | 18.17 | 30.5256 | 10.902 | 5.0876 | 72.68
5 | Deployment |  | 0.316 | 0.316 | 0.948 | 1.896 | 2.528 | 0.316 | 6.32
6 | Customer Support |  | 0.316 | 0.316 | 1.58 | 1.896 | 1.7696 | 0.4424 | 6.32
7 | Project Management |  | 4.74 | 6.32 | 6.32 | 6.32 | 6.32 | 1.58 | 31.6
8 | Configuration Management |  | 0.632 | 0.948 | 1.58 | 1.9592 | 0.948 | 0.2528 | 6.32
9 | QA |  | 0.632 | 0.632 | 1.896 | 1.896 | 0.948 | 0.316 | 6.32
| Total |  | 24.9956 | 45.9464 | 82.476 | 105.6388 | 41.1432 | 15.8 | 316
Note on D5: Dzung Pham: Norm = 10%
Note on D6: Dzung Pham: Norm = 11%
Note on D7: Dzung Pham: Norm = 38%
Note on D8: Dzung Pham: Norm = 22% plus 1% others
Note on D9: Dzung Pham: Norm = 2%
Note on D10: Dzung Pham: Norm = 2%
Note on D11: Dzung Pham: Norm = 10%
Note on D12: Dzung Pham: Norm = 2%
Note on D13: Dzung Pham: Norm = 2%
Note on D44: mintes01: Should be zero if project done in HCMC

## Risk Assessment
Risk Assessment
# | Risk souce | Risk condition | Consequence | Prob | Impact | Priority | Mitigation plan | Contingency plan | Triggers | Assignee
3
4
5
| Note | This sheet is for assessment of the total risk buffer for the project.
The risk mitigation efforts should be calculated manually based on the risk assessment and then input to the "WBS Estimation" sheet
There is no guideline for calculation risk mitigation buffer yet.
Note on A4: Use this column as the risk identifier which allows each risk to be uniquely identified.
Note on B4: Use this column to identify unclear criteria (Select from Riskfactorchart)
Note on C4: Use this column to capture the "likely cause" of the risk. Be detailed enough so that you can start forming mitigation plans.
Note on D4: Use this column to capture the result of the risk, should it happen. If the consequences cannot be mitigated, you will have to dealt with them in a contingency plan.
Note on E4: Use this column to estimate the probability the risk will occur. - High -Medium -Low
Note on F4: Use this column to estimate the amount of impact or severity of the risk. Use schedule delay or efforts as a estimation unit.
Note on G4: Use this column to rank risks. Priority is the overall threat of the risk to the project, balancing the likelihood of actual loss with the magnitude of the potential loss (value: from 1 to 5 and 1 is the highest)
Note on H4: Use this column to document how the team is planning to prevent the risk or to lower the impact ahead of time. It may require a more detailed plan written up separately. If threshold is as follows : -Estimated impact is big - or Probality is high) -->we should have mitigation plans The cost of mitigation actions can be included into the estimate.
Note on I4: Use this column to identify what would have to be done if the risk were to become reality. This may require a more detailed plan documented separately.
Note on J4: Use this column to identify what would prompt you to execute the contingency plan. A trigger is usually a date or some sort of criteria
Note on K4: Use this column to identify who on the team is responsible for tracking this risk and its changes in probability and impact. The assignee is ot necessarily the person responsible for solving the problem, as risks often require escalation outside the team.

## Q&A
Questions Log
Questions raised by Harvey Nash Team |  |  |  |  | Responses by Client or Onsite Managers
Ref. | Raised By | Date Raised | Category | Description | Response by | Response | Date Closed
Q1
Q2
Q3
Q4
Q5
Q6
Q7
Q8
Q9
Q10
Q11
Q12
Q13
Q14
Q15
Q16
Q17
Q18
Q19
Q20
Q21
Q22
Q23
Q24
Q25
Q26
Q27
Q28
Q29
Q30
Note on F4: Enter Action owner

## Record of Changes
Record of change
Effective Date | Version | Change location | Change description | Reference
2012-02-16 | 0.1 | All | First draft
2012-02-21 | 1.0