## Summary
WBS Estimate for |  | Product and Channel Review
Version |  | 1.0 | Date | 2012-04-10
Estimated by |  | Quyen Nguyen | Approved by
Red Hat Approval date
Note: Fill up the cells with white colour only
I. Estimates
1. Total Project Effort (person days) |  | 276
2. Project Duration (months) |  | Max duration |  | max duration that will not impact the quality and the estimate
|  | Min duration |  | min duration that will not impact the quality and the estimate
|  | Suggested duration | 19 weeks | This is the suggested duration for optimal project quality
II. Scope & Assumptions
1. In scope
The scope for estimate does include the following items:
Item |  |  |  | Note
Refer to the session "In Scope" of the BCR 1779 19-03-2012v0.3.pdf document
1
2
3
4
Please refer to "WBS Estimation" for the detailed list of scope items
2. Out of scope
The estimate does not include the following items:
Item |  | Reason |  | Note
1 | Refer to the session "Out of Scope" of the BCR 1779 19-03-2012v0.3.pdf document
2
3
3. Input from Client
The following input are expected to be provided by the customer
Item |  |  | Expected date
1
2
4. Risks
For all the identified risks please refer to risk assessment sheet
For the breakdown of efforts for risk mitigation, please see in "WBS Estimation" sheet
5. Onsite visits and other expenses
The following onsite visits and expenses are expected
Item |  |  | Expected cost
1
2
3
6. Others assumptions
1 | Using the CXF build and develop a web service: http://cxf.apache.org/
2 | Using the Hibernate create a persistence layer
3 | Data base design for this project was available. Databases backup will be provided by CPF in clarifying requirement phase
4 | The requirement now does not mention that how to use input params to response output params. However, we assume that some fields can get directly from database, some fields we need to calculate and the calculation may be complicated.
III. Milestone Plan
ID | Title/Description | Date | Deliverables | Dependencies
M0 | Kick-Off | D | Meeting minutes | Contract signed
M1 | Project Initiation Finished | D+2.0 weeks | Agreed PID, Full requirements | M0, all parties approve PID, Full requirements
M2 | Requirement&Design Finished | D+6.0 weeks | Detail design document | M1
M3 | Coding Finished | D+12.0 weeks | Software package | M2
M4 | Testing Finished | D+13.0 weeks | Software package, Test report | M3
M5 | UAT Finish | D+15.0 weeks | Software package | M4
M6 | Warranty Finish | D+19.0 weeks | Software package | M5
Note on C22: t: We do not expect to input the full scope specification here, instead we refer to some document or email and also the detailed WBS Estimation sheet.
Note on C33: t: This is the list of key out of scope items for those we have a feeling that client may assume that they are in scope. Sample list of out of scope items: - Data migration - Data error correction - User's help - End users training - Testing the web based system in more than <specific number> of standard browsers.
Note on D70: t: mandatory
Note on D71: t: mandatory

## WBS Estimation
WBS Approach for Estimation for Product and Channel Review
Note: Fill up the cells with white colour only
Step 1: Estimate Coding & Unit Test Effort
| Total Coding & Unit Test Effort | 95.375 |  | person days
# | Task Name | Coding Effort | Total Effort | PM | BA | TL & SA | QA | Dev | Tester | Others | Remarks
1 | Rates Request |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1 | Persistence layer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.1 | Create entity classes | 0.375 | 0.10852 | 0.10852 | [6 empty] | Model entity classes map with a table or result query data from datatabase
1.1.2 | Create DAO interface, Implement | 1.5 | 0.43408 | 0.43408
1.1.3 | Write JUnit test functions in DAO | 1 | 0.28938 | 0.28938
1.2 | Web Service |  | 0 | 0
1.2.1 | Define JAVA request, response classes | 1 | 0.28938 | 0.28938 | [6 empty] | Define XML Schema (XSD ) file includes the request, response entities and elements. Using the JAXB tool generate to JAVA classes
1.2.2 | Create WSDL file | 0.5 | 0.14469 | 0.14469
1.2.3 | Validate request | 1 | 0.28938 | 0.28938
1.2.4 | Success response message | 0.75 | 0.21704 | 0.21704
1.2.5 | Failure response message for data sent by the broker | 0.5 | 0.14469 | 0.14469
1.2.6 | Failure response message from system validators | 0.25 | 0.072346 | 0.072346
1.2.7 | Unit Testing | 1 | 0.28938 | 0.28938
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Loan Quote Request |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Persistence layer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1.1 | Create entity classes | 0.375 | 1.0852 | 0.10852 | 0.10852 | 0.11937 | 0 | 0.41237 | 0.24959 | 0.086815 | Model entity classes map with a table or result query data from datatabase
2.1.2 | Create DAO interface, Implement | 1.5 | 4.3408 | 0.43408 | 0.43408 | 0.47748 | 0 | 1.6495 | 0.99837 | 0.34726
2.1.3 | Write JUnit test functions in DAO | 1 | 2.8938 | 0.28938 | 0.28938 | 0.31832 | 0 | 1.0997 | 0.66558 | 0.23151
2.2 | Web Service |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2.1 | Define JAVA request, response classes | 1 | 2.8938 | 0.28938 | 0.28938 | 0.31832 | 0 | 1.0997 | 0.66558 | 0.23151 | Define XML Schema (XSD ) file includes the request, response entities and elements. Using the JAXB tool generate to JAVA classes
2.2.2 | Create WSDL file | 0.5 | 1.4469 | 0.14469 | 0.14469 | 0.15916 | 0 | 0.54983 | 0.33279 | 0.11575
2.2.3 | Validate request | 1.5 | 4.3408 | 0.43408 | 0.43408 | 0.47748 | 0 | 1.6495 | 0.99837 | 0.34726
2.2.4 | Success response message | 1 | 2.8938 | 0.28938 | 0.28938 | 0.31832 | 0 | 1.0997 | 0.66558 | 0.23151
2.2.5 | Failure response message for data sent by the broker | 1 | 2.8938 | 0.28938 | 0.28938 | 0.31832 | 0 | 1.0997 | 0.66558 | 0.23151
2.2.6 | Failure response message from system validators | 0.25 | 0.72346 | 0.072346 | 0.072346 | 0.079581 | 0 | 0.27491 | 0.1664 | 0.057877
2.2.7 | Unit Testing | 1 | 2.8938 | 0.28938 | 0.28938 | 0.31832 | 0 | 1.0997 | 0.66558 | 0.23151
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Loan Creation Request (includes Facility Fee service) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1 | Persistence layer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.1 | Create entity classes | 0.5 | 1.4469 | 0.14469 | 0.14469 | 0.15916 | 0 | 0.54983 | 0.33279 | 0.11575 | Model entity classes map with a table or result query data from datatabase
3.1.2 | Create DAO interface, Implement | 2 | 5.7877 | 0.57877 | 0.57877 | 0.63664 | 0 | 2.1993 | 1.3312 | 0.46301
3.1.3 | Write JUnit test functions in DAO | 1.5 | 4.3408 | 0.43408 | 0.43408 | 0.47748 | 0 | 1.6495 | 0.99837 | 0.34726
3.2 | Web Service |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2.1 | Define JAVA request, response classes | 1.5 | 4.3408 | 0.43408 | 0.43408 | 0.47748 | 0 | 1.6495 | 0.99837 | 0.34726 | Define XML Schema (XSD ) file includes the request, response entities and elements. Using the JAXB tool generate to JAVA classes
3.2.2 | Create WSDL file | 0.5 | 1.4469 | 0.14469 | 0.14469 | 0.15916 | 0 | 0.54983 | 0.33279 | 0.11575
3.2.3 | Validate request | 2.5 | 7.2346 | 0.72346 | 0.72346 | 0.79581 | 0 | 2.7491 | 1.664 | 0.57877
3.2.4 | Success response message | 1 | 2.8938 | 0.28938 | 0.28938 | 0.31832 | 0 | 1.0997 | 0.66558 | 0.23151
3.2.5 | Failure response message for data sent by the broker | 3 | 8.6815 | 0.86815 | 0.86815 | 0.95497 | 0 | 3.299 | 1.9967 | 0.69452
3.2.6 | Failure response message from system validators | 0.5 | 1.4469 | 0.14469 | 0.14469 | 0.15916 | 0 | 0.54983 | 0.33279 | 0.11575
3.2.7 | Unit Testing | 2 | 5.7877 | 0.57877 | 0.57877 | 0.63664 | 0 | 2.1993 | 1.3312 | 0.46301
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Redemption Quote Request |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1 | Persistence layer |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.1.1 | Create entity classes | 0.375 | 1.0852 | 0.10852 | 0.10852 | 0.11937 | 0 | 0.41237 | 0.24959 | 0.086815 | Model entity classes map with a table or result query data from datatabase
4.1.2 | Create DAO interface, Implement | 1.5 | 4.3408 | 0.43408 | 0.43408 | 0.47748 | 0 | 1.6495 | 0.99837 | 0.34726
4.1.3 | Write JUnit test functions in DAO | 1 | 0.28938 | 0.28938
4.2 | Web Service |  | 0 | 0
4.2.1 | Define JAVA request, response classes | 1 | 0.28938 | 0.28938 | [6 empty] | Define XML Schema (XSD ) file includes the request, response entities and elements. Using the JAXB tool generate to JAVA classes
4.2.2 | Create WSDL file | 0.5 | 1.4469 | 0.14469 | 0.14469 | 0.15916 | 0 | 0.54983 | 0.33279 | 0.11575
4.2.3 | Validate request | 1.5 | 0.43408 | 0.43408
4.2.4 | Success response message | 1 | 0.28938 | 0.28938
4.2.5 | Failure response message for data sent by the broker | 1 | 0.28938 | 0.28938
4.2.6 | Failure response message from system validators | 0.25 | 0.072346 | 0.072346
4.2.7 | Unit Testing | 1 | 0.28938 | 0.28938
|  |  | 0 | 0
5 | Amend Payment Schedule Request |  | 0 | 0
5.1 | Persistence layer |  | 0 | 0
5.1.1 | Create entity classes | 0.375 | 0.10852 | 0.10852 | [6 empty] | Model entity classes map with a table or result query data from datatabase
5.1.2 | Create DAO interface, Implement | 1.5 | 0.43408 | 0.43408
5.1.3 | Write JUnit test functions in DAO | 1 | 0.28938 | 0.28938
5.2 | Web Service |  | 0 | 0
5.2.1 | Define JAVA request, response classes | 1 | 0.28938 | 0.28938 | [6 empty] | Define XML Schema (XSD ) file includes the request, response entities and elements. Using the JAXB tool generate to JAVA classes
5.2.2 | Create WSDL file | 0.5 | 0.14469 | 0.14469
5.2.3 | Validate request | 1.5 | 0.43408 | 0.43408
5.2.4 | Success response message | 1 | 0.28938 | 0.28938
5.2.5 | Failure response message for data sent by the broker | 1 | 0.28938 | 0.28938
5.2.6 | Failure response message from system validators | 0.25 | 0.072346 | 0.072346
5.2.7 | Unit Testing | 1 | 0.28938 | 0.28938
|  |  | 0 | 0
6 | Cancellation Request |  | 0 | 0
6.1 | Persistence layer |  | 0 | 0
6.1.1 | Create entity classes | 0.375 | 0.10852 | 0.10852 | [6 empty] | Model entity classes map with a table or result query data from datatabase
6.1.2 | Create DAO interface, Implement | 1.5 | 0.43408 | 0.43408
6.1.3 | Write JUnit test functions in DAO | 1 | 0.28938 | 0.28938
6.2 | Web Service |  | 0 | 0
6.2.1 | Define JAVA request, response classes | 1 | 0.28938 | 0.28938 | [6 empty] | Define XML Schema (XSD ) file includes the request, response entities and elements. Using the JAXB tool generate to JAVA classes
6.2.2 | Create WSDL file | 0.5 | 0.14469 | 0.14469
6.2.3 | Validate request | 1.5 | 0.43408 | 0.43408
6.2.4 | Success response message | 1 | 0.28938 | 0.28938
6.2.5 | Failure response message for data sent by the broker | 1 | 0.28938 | 0.28938
6.2.6 | Failure response message from system validators | 0.25 | 0.072346 | 0.072346
6.2.7 | Unit Testing | 1 | 0.28938 | 0.28938
|  |  | 0 | 0
7 | Change of Address Request |  | 0 | 0
7.1 | Persistence layer |  | 0 | 0
7.1.1 | Create entity classes | 0.375 | 0.10852 | 0.10852 | [6 empty] | Model entity classes map with a table or result query data from datatabase
7.1.2 | Create DAO interface, Implement | 1.5 | 0.43408 | 0.43408
7.1.3 | Write JUnit test functions in DAO | 1 | 0.28938 | 0.28938
7.2 | Web Service |  | 0 | 0
7.2.1 | Define JAVA request, response classes | 1 | 0.28938 | 0.28938 | [6 empty] | Define XML Schema (XSD ) file includes the request, response entities and elements. Using the JAXB tool generate to JAVA classes
7.2.2 | Create WSDL file | 0.5 | 0.14469 | 0.14469
7.2.3 | Validate request | 1.5 | 0.43408 | 0.43408
7.2.4 | Success response message | 1 | 0.28938 | 0.28938
7.2.5 | Failure response message for data sent by the broker | 1 | 0.28938 | 0.28938
7.2.6 | Failure response message from system validators | 0.25 | 0.072346 | 0.072346
7.2.7 | Unit Testing | 1 | 0.28938 | 0.28938
|  |  | 0 | 0
8 | CHANGE OF BANK DETAILS REQUEST |  | 0 | 0
8.1 | Persistence layer |  | 0 | 0
8.1.1 | Create entity classes | 0.375 | 0.10852 | 0.10852 | [6 empty] | Model entity classes map with a table or result query data from datatabase
8.1.2 | Create DAO interface, Implement | 1.5 | 0.43408 | 0.43408
8.1.3 | Write JUnit test functions in DAO | 1 | 0.28938 | 0.28938
8.2 | Web Service |  | 0 | 0
8.2.1 | Define JAVA request, response classes | 1 | 0.28938 | 0.28938 | [6 empty] | Define XML Schema (XSD ) file includes the request, response entities and elements. Using the JAXB tool generate to JAVA classes
8.2.2 | Create WSDL file | 0.5 | 0.14469 | 0.14469
8.2.3 | Validate request | 1.5 | 0.43408 | 0.43408
8.2.4 | Success response message | 1 | 0.28938 | 0.28938
8.2.5 | Failure response message for data sent by the broker | 1 | 0.28938 | 0.28938
8.2.6 | Failure response message from system validators | 0.5 | 0.14469 | 0.14469
8.2.7 | Unit Testing | 1 | 0.28938 | 0.28938
|  |  | 0 | 0
9 | Mid Term Adjustment Request |  | 0 | 0
9.1 | Persistence layer |  | 0 | 0
9.1.1 | Create entity classes | 0.375 | 0.10852 | 0.10852 | [6 empty] | Model entity classes map with a table or result query data from datatabase
9.1.2 | Create DAO interface, Implement | 1.5 | 0.43408 | 0.43408
9.1.3 | Write JUnit test functions in DAO | 1 | 0.28938 | 0.28938
9.2 | Web Service |  | 0 | 0
9.2.1 | Define JAVA request, response classes | 1 | 0.28938 | 0.28938 | [6 empty] | Define XML Schema (XSD ) file includes the request, response entities and elements. Using the JAXB tool generate to JAVA classes
9.2.2 | Create WSDL file | 0.5 | 0.14469 | 0.14469
9.2.3 | Validate request | 1.5 | 0.43408 | 0.43408
9.2.4 | Success response message | 1 | 0.28938 | 0.28938
9.2.5 | Failure response message for data sent by the broker | 1 | 0.28938 | 0.28938
9.2.6 | Failure response message from system validators | 0.5 | 0.14469 | 0.14469
9.2.7 | Unit Testing | 1 | 0.28938 | 0.28938
|  |  | 0 | 0
10 | REPORT REQUEST |  | 0 | 0
10.1 | Persistence layer |  | 0 | 0
10.1.1 | Create entity classes | 0.375 | 0.10852 | 0.10852 | [6 empty] | Model entity classes map with a table or result query data from datatabase
10.1.2 | Create DAO interface, Implement | 1.5 | 0.43408 | 0.43408
10.1.3 | Write JUnit test functions in DAO | 1 | 0.28938 | 0.28938
10.2 | Web Service |  | 0 | 0
10.2.1 | Define JAVA request, response classes | 1 | 0.28938 | 0.28938 | [6 empty] | Define XML Schema (XSD ) file includes the request, response entities and elements. Using the JAXB tool generate to JAVA classes
10.2.2 | Create WSDL file | 0.5 | 0.14469 | 0.14469
10.2.3 | Validate request | 1 | 0.28938 | 0.28938
10.2.4 | Success response message | 1 | 0.28938 | 0.28938
10.2.5 | Failure response message for data sent by the broker | 0.5 | 0.14469 | 0.14469
10.2.6 | Failure response message from system validators | 0.25 | 0.072346 | 0.072346
10.2.7 | Unit Testing | 1 | 0.28938 | 0.28938
|  |  | 0 | 0
| <insert additional lines BEFORE this mark> |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total (man days) | 95.375 | 96.6181 | 27.6 | 27.6 | 30.36 | 0 | 104.88 | 63.48 | 22.08
| Total (man hours) |  | 772.9447 | 220.8 | 220.8 | 242.88 | 0 | 839.04 | 507.84 | 176.64
Step 2: Estimate Total Project Effort before Risk Mitigation
| Total Project Effort before risk mitigation | 250.9868 |  | person days
Effort Distribution by Process for this project
| Software Process Name | Effort | Distr. | In Scope | Remarks
1 | Requirement | 25.0987 | 10% | Y | < All efforts by process' items during all phases of the development , including UAT & warranty>
2 | Design | 27.6086 | 11% | Y
3 | Coding & Unit test | 95.375 | 38% | Y | < Including Unit testing done by developers >
4 | Test | 57.727 | 23% | Y
5 | Deployment | 5.0197 | 2% | Y
6 | Customer Support | 5.0197 | 2% | Y
7 | Project Management | 25.0987 | 10% | Y
8 | Configuration Management | 5.0197 | 2% | Y
9 | QA | 5.0197 | 2% | Y
100%
Step 3: Mitigation for Named Risks
| Total Mitigation Efforts | 12.5493 | 5%
Detailed Risk Mitigation Efforts
| Risk | Man.day | % | Remarks
1 | Requirement is not yet clear | 12.5493 | 5% | < please be detailed and specific >
2 |  | 0 | 0% | <don't add risk buffer for unforseen risk, unless agreed with client >
3 |  | 0 | 0% | < best practice is to budget efforts for risk prevention and mitigation + make clear with client on the plan for correction when the risk becomes an issue>
4 |  | 0 | 0% | <Suggested total risk mitigation efforts 5%-20% for WBS estimates>
5 |  | 0 | 0%
6 |  | 0 | 0%
Step 4: SDC Programme Management |  | Man.day | %
| Total SDC efforts | 12.5493 | 5% | Remarks
1 | Offshore SDC PM | 12.5493 | 5% | For projects with third party supplier, Harvey Nash offshore efforts will be estimated separately here 5% of total efforts or 1.5 days per week should be a norm for a typical development project with 1 Offshore PM
2 |  | 0 | 0%
Step 5: Additional and Specific Effort
| Additional effort | Man.day | % | Remarks
|  | 0 | 0%
1
2
3 |  | 0
4 |  | 0
Step 6: Calculate Total Project Effort
| Total Project Effort | 276 |  | person days | [6 empty] | 38%
Note on E162: Dzung Pham: Project effort distribution
Note on E163: Dzung Pham: Norm = 10%
Note on E164: Dzung Pham: Norm = 11%
Note on E165: Dzung Pham: Norm = 38%
Note on E166: Dzung Pham: Norm = 22% plus 1% others
Note on E167: Dzung Pham: Norm = 2%
Note on E168: Dzung Pham: Norm = 2%
Note on E169: Dzung Pham: Norm = 10%
Note on E170: Dzung Pham: Norm = 2%
Note on E171: Dzung Pham: Norm = 2%
Note on E179: Truong: Percentage of effort buffered for risk mitigation. Buffer for correction when the risk became an issue should be discussed in assumptions (summary sheet)

## Effort Breakdown
A | WBS Effort Distribution
Effort distribution by processes (norm)
ID | Software Process Name | Distr. | In scope
1 | Requirement | 0.1 | Y
2 | Design | 0.11 | Y
3 | Coding & Unit test | 0.38 | Y
4 | Test | 0.23 | Y
5 | Deployment | 0.02 | Y
6 | Customer Support | 0.02 | Y
7 | Project Management | 0.1 | Y
8 | Configuration Management | 0.02 | Y
9 | QA | 0.02 | Y
100%
Effort distribution by processes and stages (norm)
For New development projects
|  |  | Initiation | Definition | Solution | Construction | Transition | Termination | Check
| Process | [6 empty] | (Warranty)
1 | Requirement |  | 25% | 40% | 20% | 10% | 5% | 0% | 100%
2 | Design |  | 10% | 20% | 45% | 20% | 5% | 0% | 100%
3 | Coding & Unit test |  | 4% | 10% | 25% | 42.5% | 12% | 6.5% | 100%
4 | Test |  | 3% | 8% | 25% | 42% | 15% | 7% | 100%
5 | Deployment |  | 5% | 5% | 15% | 30% | 40% | 5% | 100%
6 | Customer Support |  | 5% | 5% | 25% | 30% | 28% | 7% | 100%
7 | Project Management |  | 15% | 20% | 20% | 20% | 20% | 5% | 100%
8 | Configuration Management |  | 10% | 15% | 25% | 31% | 15% | 4% | 100%
9 | QA |  | 10% | 10% | 30% | 30% | 15% | 5% | 100%
| Total |  | 7.91% | 14.54% | 26.1% | 33.43% | 13.02% | 5% | 100%
B | WBS Effort Breakdown
| Total project efforts | 276
| Role | Person days | Person hours | Remarks
| SDC PM | 5 | 40 | aproximation only
| PM | 27 | 216 | aproximation only
| BA | 33 | 264 | aproximation only
| TL & SA | 35 | 280 | aproximation only
| QA | 11 | 88 | aproximation only
| Senior Dev | 21 | 168 | aproximation only
| Dev | 82 | 656 | aproximation only
| Senior Tester | 12 | 96 | aproximation only
| Tester | 50 | 400 | aproximation only
| Total Effort | 276 | 2208 | aproximation only
Efforts by phases
| Phase | Total | Initiation | Definition | Solution | Construction | Transition | Termination (warranty) |  | Remarks
| Person days | 276 | 21.8316 | 40.1304 | 72.036 | 92.2668 | 35.9352 | 13.8 |  | aproximation only
| Person hours | 2208 | 174.6528 | 321.0432 | 576.288 | 738.1344 | 287.4816 | 110.4 |  | aproximation only
Detailed Efforts Breakdown by Process Item over Stages (person days)
|  |  | Initiation | Definition | Solution | Construction | Transition | Termination | Checksum
| Process | [6 empty] | (Warranty)
1 | Requirement |  | 6.9 | 11.04 | 5.52 | 2.76 | 1.38 | 0 | 27.6
2 | Design |  | 3.036 | 6.072 | 13.662 | 6.072 | 1.518 | 0 | 30.36
3 | Coding & Unit test |  | 4.1952 | 10.488 | 26.22 | 44.574 | 12.5856 | 6.8172 | 104.88
4 | Test |  | 1.9044 | 5.0784 | 15.87 | 26.6616 | 9.522 | 4.4436 | 63.48
5 | Deployment |  | 0.276 | 0.276 | 0.828 | 1.656 | 2.208 | 0.276 | 5.52
6 | Customer Support |  | 0.276 | 0.276 | 1.38 | 1.656 | 1.5456 | 0.3864 | 5.52
7 | Project Management |  | 4.14 | 5.52 | 5.52 | 5.52 | 5.52 | 1.38 | 27.6
8 | Configuration Management |  | 0.552 | 0.828 | 1.38 | 1.7112 | 0.828 | 0.2208 | 5.52
9 | QA |  | 0.552 | 0.552 | 1.656 | 1.656 | 0.828 | 0.276 | 5.52
| Total |  | 21.8316 | 40.1304 | 72.036 | 92.2668 | 35.9352 | 13.8 | 276
Note on D5: Dzung Pham: Norm = 10%
Note on D6: Dzung Pham: Norm = 11%
Note on D7: Dzung Pham: Norm = 38%
Note on D8: Dzung Pham: Norm = 22% plus 1% others
Note on D9: Dzung Pham: Norm = 2%
Note on D10: Dzung Pham: Norm = 2%
Note on D11: Dzung Pham: Norm = 10%
Note on D12: Dzung Pham: Norm = 2%
Note on D13: Dzung Pham: Norm = 2%
Note on D44: mintes01: Should be zero if project done in HCMC

## Risk Assessment
Risk Assessment
# | Risk souce | Risk condition | Consequence | Prob | Impact | Priority | Mitigation plan | Contingency plan | Triggers | Assignee
3
4
5
| Note | This sheet is for assessment of the total risk buffer for the project.
The risk mitigation efforts should be calculated manually based on the risk assessment and then input to the "WBS Estimation" sheet
There is no guideline for calculation risk mitigation buffer yet.
Note on A4: Use this column as the risk identifier which allows each risk to be uniquely identified.
Note on B4: Use this column to identify unclear criteria (Select from Riskfactorchart)
Note on C4: Use this column to capture the "likely cause" of the risk. Be detailed enough so that you can start forming mitigation plans.
Note on D4: Use this column to capture the result of the risk, should it happen. If the consequences cannot be mitigated, you will have to dealt with them in a contingency plan.
Note on E4: Use this column to estimate the probability the risk will occur. - High -Medium -Low
Note on F4: Use this column to estimate the amount of impact or severity of the risk. Use schedule delay or efforts as a estimation unit.
Note on G4: Use this column to rank risks. Priority is the overall threat of the risk to the project, balancing the likelihood of actual loss with the magnitude of the potential loss (value: from 1 to 5 and 1 is the highest)
Note on H4: Use this column to document how the team is planning to prevent the risk or to lower the impact ahead of time. It may require a more detailed plan written up separately. If threshold is as follows : -Estimated impact is big - or Probality is high) -->we should have mitigation plans The cost of mitigation actions can be included into the estimate.
Note on I4: Use this column to identify what would have to be done if the risk were to become reality. This may require a more detailed plan documented separately.
Note on J4: Use this column to identify what would prompt you to execute the contingency plan. A trigger is usually a date or some sort of criteria
Note on K4: Use this column to identify who on the team is responsible for tracking this risk and its changes in probability and impact. The assignee is ot necessarily the person responsible for solving the problem, as risks often require escalation outside the team.

## Q&A
Questions Log
Questions raised by Harvey Nash Team |  |  |  |  | Responses by Client or Onsite Managers
Ref. | Raised By | Date Raised | Category | Description | Response by | Response | Date Closed
Q1 | Quyen | 2012-04-10 |  | Which are the application servers using to deploy a web service? a. Apache Service Mix b. Apache Tomcat c. Jboss d. ….
Q2 | Quyen | 2012-04-10 |  | Do you have a framework or technology stack to implement a web service? a. Yes, please send this source code of the framework or the technology stack document to us study before implementing. b. No, we suggest a technology stack to implement a web service module: - Apache CXF - Apache Service Mix http://cxf.apache.org/ http://camel.apache.org/ http://servicemix.apache.org/
Q3 | Quyen | 2012-04-10 |  | Which the service transport will be used HTTP or HTTPS?
Q4
Q5
Q6
Q7
Q8
Q9
Q10
Q11
Q12
Q13
Q14
Q15
Q16
Q17
Q18
Q19
Q20
Q21
Q22
Q23
Q24
Q25
Q26
Q27
Q28
Q29
Q30
Note on F4: Enter Action owner

## Record of Changes
Record of change
Effective Date | Version | Change location | Change description | Reference
2012-04-10 | 1.0 | All | First version