## Sheet1
|  | 2011-11-23 | 2011-11-24 | 2011-11-25 | 2011-11-26 | 2011-11-27 | 2011-11-28 | 2011-11-29 | 2011-11-30 | 2011-12-01 | 2011-12-02 | 2011-12-03 | 2011-12-04 | 2011-12-05 | 2011-12-06 | 2011-12-07 | 2011-12-08 | 2011-12-09 | 2011-12-10 | 2011-12-11 | 2011-12-12 | 2011-12-13 | 2011-12-14 | 2011-12-15 | 2011-12-16 | 2011-12-17 | 2011-12-18 | 2011-12-19 | 2011-12-20 | 2011-12-21 | 2011-12-22 | 2011-12-23 | 2011-12-24 | 2011-12-25 | 2011-12-26 | 2011-12-27 | 2011-12-28 | 2011-12-29 | 2011-12-30 | 2011-12-31
nhanld | Template for prototype | bar: 2011-11-23
dungnm2, hungnm | Spring dependency | bar: 2011-11-23; 2011-11-26
hant21, phongpv | Hibernate | bar: 2011-11-23; 2011-11-26
all | Prototypes | 2011-11-24: 1; 2011-11-25: 0.5
all | Design database | 2011-11-25: 0.5
| demo hibernate | 2011-11-27: 0.5
| demo spring | 2011-11-27: 0.5
all | High level design | 2011-11-27: 0.5
Detail design (class, sequence diagram, pseudo-code)
nhanld | 6.1 - Login, Menu | 2011-11-28: 1; 2011-11-29: 0.5
hungnm | 6.2 - Organisation - List, add, amend, mark
6.2 - Supporting Materials - List, add, amend, mark
6.2 - Directorates - List, add, amend, mark
6.2 - Department - List, add, amend, mark
6.2 - Team - List, add, amend, mark
6.3 - Service -List, add, amend, mark
6.3 - Programme -List, add, amend, mark
6.4 - Trust Region -List, add, amend, mark
6.4 - Trust District -List, add, amend, mark
6.4 - Gov Office - List
6.5 - Premise -List, add, amend, mark
6.5 - Facility -List, add, amend, mark
6.5 - Volunteering -List, add, amend, mark
6.5 - Minor Work Projects -List, add, amend, mark
6.6 - Contact -List, add, amend, mark
6.7 - Address lookup
6.8 - Type of Business lookup
Class, Sequence digaram
Pseudo-code
Prepare for Unit testing
Code
Self code review
Peer code review
Prepare UT script
Perform UT and fix bug

## Sheet2
Project package structure |  | Technologies | Requirement
3 stages: M-V-C |  | Eclipse 3.7 | In-active button => radio buttons
com.models |  | Jdk 1.6 |  | Apears in Detail window
| com.models.module1 | Tomcat 7
com.models.module2
com.views
com.views.module1
com.views.module2
com.controllers
com.controllers.module1
com.controllers.module2